## Sheet1
ekuuh; eq[;ea=h }kjk ;kstukvksa dk fd;s x;s f'kykU;kl dh lwph miyC/k djkus ds laca/k esaA
S.No. | Nodal Department | Foundation stone laid project name | Estimated Project Cost (Pls use the following format XX,XX,XX,XXX) | Date of Foundation stone laid by hon'ble CM (DD/MM/YYYY | District | Block/ULB | Panchayat/Ward | DPR Approval Date (dd/mm/yyyy) | Administrative Approval date (dd/mm/yyyy) | Technical Sanction date (dd/mm/yyyy) | Tender Floationg date (dd/mm/yyyy) | Work Order Date (dd/mm/yyyy) | Project completion Time (in months | Sanctioned project cost (Pls Use the following format (XX,XX,XX,XXX) | Implementing agency (Name of directorate, Corporation District, Block, etc.) | Total Expenditure so far (Pls Use the following format XX,XX,XX,XXX) | Estimated Physical Progress of Project (In percentage) | Estimated financial progress of Project (In percentage) | Estimated Completion time (mm/yyyy) | Challenges/ Obstacles Pls Note if any
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | RMC | Improvement of PCC and Bituminous Road from Kanke main Road to MP Mahesh Poddar House with drain under Ward No- 01 | 10129800 | 2020-11-29 | Ranchi | RMC | 1 | - | 2019-10-31 | - | 2020-01-03 | 2020-11-09 | 9 Months | 9114472 | M/s RV Construction | 6868864 | 100% | 100% | - | -
2 | RMC | Construction of PCC Road and RCC Drain at Shankarpuram Edalhatu & from LIC board to BNP Singh house under Ward No- 02 | 19127300 | 2020-11-29 | Ranchi | RMC | 2 | - | 2019-10-31 | - | 2020-01-03 | 2020-11-25 | 9 Months | 17211333 | M/s Baba Jharkhand Dham Construction | 12497787 | 100% | 100% | - | -
3 | RMC | Construction of RCC Drain with precast RCC Slab from Bariatu road NH via Kamal nayan apartment (Gautambudh Marg) to the existing RCC Drain towards DIG ground with road raising in 350’ length and Construction of RCC Drain and PCC Road from Govt. High school bariatu in gautambudh marg towards the house of lakaraji under Ward No- 19 | 4545200 | 2020-12-02 | Ranchi | RMC | 19 | - | 2019-10-31 | - | 2020-01-03 | 2020-11-12 | 6 Months | 4090356 | Dhananjay Singh | 4310714 | 100% | 100% | - | -
4 | RMC | Improvement of PCC Road with Bituminous in Harmu House Colony B type qtr to Om Shakti Chatt Ghat under Ward No- 26 | 12945800 | 2020-12-04 | Ranchi | RMC | 26 | - | 2019-02-21 | - | 2020-01-03 | 2020-11-09 | 9 Months | 14607678 | Bhagwati Developers & Const. | 12637749 | 100% | 80% | - | -
5 | RMC | Improvement of Existing CC Pavement & Construction of RCC Covered drain, Bituminous Work and Paver Block work fro Kanke road main road (Opp CM Residence) to Police Line Gate and Kanke Main road through Electrical Office and Qtr. No- 3A under Ward No- 02 | 6890200 | 2020-12-05 | Ranchi | RMC | 2 | - | 2019-02-21 | - | 2020-01-03 | 2020-11-09 | 6 Months | 6200973 | Vinara Dwelles Engicon Pvt. Ltd. | 2641769 | 100% | 100% | - | -
6 | RMC | Construction of Road and Drain from Tank Side, St Road Budhia Shop sounding Filtration plant road remaining part of Harsher Basti and South side of Bus Stand under Ward No- 39 | 21220011 | 2020-12-04 | Ranchi | RMC | 39 | - | 2019-02-21 | - | 2020-01-03 | 2020-11-09 | 9 Months | 19388448 | Orascon Infrastructure | 20907407 | 100% | 100% | - | -
7 | RMC | Construction of RCC Drain and Improvement of Bituminous Road at Doranda from Rajendra Chowk to Gowala toil via Church Ward No- 45 | 16712300 | 2020-12-04 | Ranchi | RMC | 45 | - | 2019-10-31 | - | 2020-01-03 | 2020-11-09 | 9 Months | 16826724 | Sidra Enterprises | 16682977 | 100% | 100% | - | -
8 | RMC | Construction of PCC Road Difference area at Dhela Toli under Ward No- 09 | 4747800 | 2020-12-03 | Ranchi | RMC | 9 | - | 2019-10-31 | - | 2020-01-14 | 2020-11-07 | 6 Months | 4273011 | Satya Prakash | 4627745 | 100% | 100% | - | -
9 | RMC | Construction of PCC Road RCC Drain and Culvert at Shanti Vihar Tiril (Remaining Part) under Ward No- 09 | 4983950 | 2020-12-09 | Ranchi | RMC | 9 | - | 2019-10-31 | - | 2020-01-14 | 2020-11-09 | 6 Months | 4485542 | Rajesh Kr. Sahu | 4647505 | 100% | 100% | - | -
10 | RMC | Widening of PCC Road and Improvement of Old PCC Road to Bituminous road and Construction of RCC Drain from Gyan Ranjan Chowk to Dhobighat Murgi faram Road to Gulmohar Park Road and R. P Raja to Pankaj Jaswal at Ward No- 10 | 24949300 | 2020-12-02 | Ranchi | RMC | 10 | - | 2019-10-31 | - | 2020-01-14 | 2020-11-12 | 9 Months | 22454332 | Harendra Singh | 25545660 | 100% | 100% | - | -
11 | RMC | Construction of PCC Road, RCC Drain and Improvement of Road with Bitumen at Makchund Toli and New Makchund Toli under Ward No- 13 | 22366200 | 2020-12-01 | Ranchi | RMC | 13 | - | 2019-10-31 | - | 2020-01-14 | 2020-11-09 | 9 Months | 19994619 | M/s Gokul Construction | 21656931 | 100% | 100% | - | -
12 | RMC | Construction of RCC Drain in Both sides of Road from Bahubazar Chowk to Oxford School at Pragati Path under Ward No- 13&14 | 24979400 | 2020-12-01 | Ranchi | RMC | 13/14 | - | 2019-10-31 | - | 2020-01-14 | 2020-12-24 | 9 Months | 22481492 | Seema Const & Developers | 20160093 | 100% | 80% | - | -
13 | RMC | Construction of RCC Drain and Improvement of Road at mukti Sharan Lane under Ward No- 17 | 9993800 | 2020-12-01 | Ranchi | RMC | 17 | - | - | - | 2020-01-14 | 2020-11-09 | 6 Months | 9993886 | RB Construction | 9533197 | 100% | 100% | - | -
14 | RMC | okMZ la[;k 16 ds vUrxZr vYcVZ dSEil esa cM+k ukyk dk fuekZ.k dk;ZA | 20000000 | 2021-07-23 | Ranchi | RMC | 16 | - | 2019-02-21 | - | 2021-01-12 | 2021-06-08 | 9 Months | 16391369 | Sourish Infra Developers Pvt. Ltd | 11229161 | 100% | 80% | - | -
15 | RMC | okMZ la[;k 19 ds vUrxZr dje Vksyh pkSd ds lehi ih<+h Vksyh esa ih0 lh0 lh0 iFk dk fuekZ.k dk;ZA | 6995800 | 2021-07-23 | Ranchi | RMC | 19 | - | 2019-10-31 | - | 2021-01-12 | 2021-11-26 | 6 Months | 5443162 | M/s M.V Construction | 2558652 | 100% | 50% | - | -
16 | RMC | fcjlk eq.Mk cl VfeZuy jkWph ds fy;s igqWp iFk dk pkSM+hdj.k ,oa lqn`<+hdj.k@iquZfuekZ.k dk dk;ZA | 8370900 | 2021-07-23 | Ranchi | RMC | 13 | - | - | - | 2021-01-27 | 2021-08-03 | 6 Months | 8522245 | Shivam Construction | 1572788 | 50% | 15% | - | -
17 | RMC | okMZ la[;k 36 ds vUrxZr yktir uxj Mh0 ih0 ,l0 tqfu;j Ldwy ds pgkjfnokjh ls vkj0 lh0 ukyh ,oa ih0 lh0 lh0 iFk dk fuekZ.k dk;ZA | 8680101 | 2021-07-23 | Ranchi | RMC | 36 | - | 2021-02-25 | - | 2021-02-12 | 2021-08-16 | 9 Months | 7254226 | S&M Constrution | 7773752 | 100% | 90% | - | -
18 | RMC | okMZ la[;k 36 ds vUrxZr iqUnkx lkgq pkSd ls lkbZ fcgkj dksyksuh gksrs gq;s vkbZ0 ,l0 ,e0 pkSd ,oa veu xzhu lhVh rd iFk dk fuekZ.k dk;ZA | 8830971 | 2021-07-23 | Ranchi | RMC | 36 | - | 2021-02-25 | - | 2021-02-12 | 2021-06-28 | 9 Months | 7873797 | M/s M.V Construction | 6049263 | 100% | 80% | - | -
19 | RMC | okMZ la[;k 44 ds vUrxZr f'ko eafnj ds ikl ,0 th0 dk;kZy; eq[; ekxZ ls ysdj vkdk'k dkWEiysDl ds ikl nqxkZ eafnj ls ,0 th0 pkSd rd iFk dkyhdj.k ,oa ukyh dk lq/kkj dk;ZA | 3194814 | 2021-07-23 | Ranchi | RMC | 44 | - | 2021-01-28 | - | 2021-02-12 | 2021-06-28 | 6 Months | 2927318 | M/s Webuild Infracon Pvt. Ltd. | 2823728 | 100% | 100% | - | -
20 | RMC | jkWph uxj fuxe {ks=kUrxZr t;iky flg LVsfM;e ds iquZfodkl dk dk;ZA | 45304500 | 2021-07-23 | Ranchi | RMC | 18 | - | 2021-02-19 | - | 2021-03-02 | 2021-06-21 | 12 Months | 43072680 | Rewant Engineer Construction Company Pvt Ltd. | 5388022 | 100% | 100% | - | -
21 | RMC | jkWph uxj fuxe {ks=kUrxZr cM+k rkykc Qst&01 dk iquZfodkl dk dk;ZA | 48959895 | 2021-07-23 | Ranchi | RMC | 21 | - | 2016-02-25 | - | 2021-03-26 | 2021-06-14 | 12 Months | 48634766 | Brijendra Pratap singh | 48634766 | 100% | 100% | - | -
22 | RMC | jkWph uxj fuxe {ks=kUrxZr gsgy iksLV vkWfQl ,u0 ,p0&75] flVh VªLV gkWfLiVy] ,u0 ,p0&23 ds nksusk vksj fiLdk eksM+ gksrs gq;s nsoh eaMi jksM] jkrq jksM] U;w ekdsZV pkSd ds pkjks vksj isHkj CykWd yxkus dk dk;ZA | 43541254 | 2021-07-23 | Ranchi | RMC | RMC | - | 2021-03-26 | - | 2021-04-28 | 2021-07-07 | 12 Months | 48884052 | M/s Lions Construction. | 28975033 | 50% | 50% | - | -
23 | RMC | jkWph uxj fuxe {ks=kUrxZr ykbZu VSd jksM] dje Vksyh rkykc] eksjkcknh ,oa ih0 ,p0 bZ0 Mh0 pkSd] esfMdk gkWfLiVy ds lehi ,jksfcd ck;ks 'kkSpky; dk lapkyu] j[k&j[kko ,oa fuekZ.k dk dk;ZA | 41594043 | 2021-07-23 | Ranchi | RMC | RMC | - | 2020-02-17 | - | 2020-12-08 | 2021-03-20 | 15 Months | 40762943 | SMBPLUS SOLUTIONS | 7774897 | 35% | 40% | - | -
24 | RMC | jkWph uxj fuxe {ks=kUrxZr Lokeh foosdkUkUn ljksoj ¼cM+k rkykc½ dh lQkbZ ,oa ejEefr ds lkFk tSfod mipkj dk dk;ZA | 80200000 | 2021-07-23 | Ranchi | RMC | RMC | - | 2021-05-28 | - | 2021-03-19 | 2021-08-21 | - | 80200000 | JBR Technologies Limited. | 5264570 | 25% | 15% | - | -
25 | RMC | jkWph uxj fuxe {ks=kUrxZr dkads jksM esa vjcu gkV dk fuekZ.k dk;ZA | 46788849 | 2021-07-23 | Ranchi | RMC | RMC | - | - | - |  | - | - | - | - | - | - | - | - | -
26 | RMC | okMZ la[;k 02 ds vUrxZr xzhu ikdZ jksM esa vkj0 lh0 lh0 ukyh ds lkFk LySc dk fuekZ.k dk;ZA | 3813800 | 2021-07-23 | Ranchi | RMC | 2 | - | 2021-03-26 | - | 2021-06-15 | 2021-12-10 | 6 Months | 2928862 | M/s Sujeet Kumar Choudhary | 2899734 | 100% | 80% | - | -
27 | RMC | okMZ la[;k 08 ds vUrxZr v;ks/;kiqjh ds fofHkUu iFkksa esa ih0 lh0 lh0 iFk] vkj0 lh0 lh0 ukyh ,oa iqfy;k dk fuekZ.k dk;ZA | 20794300 | 2021-07-23 | Ranchi | RMC | 8 | - | 2019-02-21 | - | 2021-06-15 | 2021-09-16 | 9 Months | 19947617 | ROYAL CONSTRUCTION | 6982342 | 50% | 40% | - | -
28 | RMC | okMZ la[;k 10 ds vUrxZr ikgu Vksyh] Qsz.M~l dksyksuh ls fMLVyjh iqy rd unh@ukyk ds nksusk rjQ LVhy jsfyax yxkus dk dk;ZA | 2773900 | 2021-07-23 | Ranchi | RMC | 10 | - | 2021-03-26 | - | 2021-06-15 | - | - | - | M/s Devendra Prasad Akela | - | - | - | - | -
29 | RMC | okMZ la[;k 17 ds vUrxZr dlkbZ eqgYYkk jksM ls vktkn cLrh] bjQku ds ?kj ls fe'ku jksM rd ukyh dk fuekZ.k dk;ZA | 2876000 | 2021-07-23 | Ranchi | RMC | 17 | - | 2021-03-26 | - | 2021-06-15 | 2021-12-21 | 6 Months | 2875840 | Md Salim | 2848887 | 100% | 100% | - | -
30 | RMC | okMZ la[;k 20 ds vUrxZr lsok lnu ds ihNs cM+k yky LVªhV esa LySc ds lkFk ukyh dk fuekZ.k dk;ZA | 8954200 | 2021-07-23 | Ranchi | RMC | 20 | - | 2021-03-26 | - | 2021-06-15 | 2022-05-04 | 6 Months | 6984251 | M/s Keshav Construction | 0 | - | - | - | -
31 | RMC | okMZ la[;k 20 ds vUrxZr fiatjk iksy pkSd ls xkS'kkyk pkSd rd LySc ds lkFk ukyh fuekZ.k dk;ZA | 11685800 | 2021-07-23 | Ranchi | RMC | 20 | - | 2021-03-26 | - | 2021-06-15 | 2021-11-24 | 9 Months | 9232642 | SHASHI PRAKASH | 3598512 | 100% | 25% | - | -
32 | RMC | okMZ la[;k 20 ds vUrxZr fiatjk iksy ds fofHkUu LFkyksa ij LySc ds lkFk ukyh dk fuekZ.k dk;ZA | 11840700 | 2021-07-23 | Ranchi | RMC | 20 | - | 2021-03-26 | - | 2021-06-15 | 2021-10-27 | 9 Months | 9626372 | Barfani Mines & Minerals | 9195893 | 100% | 100% | - | -
33 | RMC | okMZ la[;k 27 ds vUrxZr flikgh th ds ?kj ls ftrsUnz ds ?kj rd ,oa Jh uxj jksM ua0&05 esa ih0 lh0 lh0 iFk ,oa vkj0 lh0 lh0 ukyh dk fuekZ.k dk;ZA | 4800000 | 2021-07-23 | Ranchi | RMC | 27 | - | - | - | 2021-06-15 | - | - | - | - | - | - | - | - | -
34 | RMC | okMZ la[;k 34 ds vUrxZr dkjesy Ldwy gksrs gq;s Mh0 ,0 Hkh0 Ldwy ls fo¦kuxj jksM ua0&02 esa iFk dkyhdj.k dk;ZA | 7000000 | 2021-07-23 | Ranchi | RMC | 34 | - | - | - | 2021-06-15 | 2021-12-13 | 6 Months | 6979284 | Sukrity Enterprises | 0 | - | - | - | -
35 | RMC | okMZ la[;k 44 ds vUrxZr okMZ ik"kZn ds ?kj ds lehi ,oa eftLVsV dksyksuh esa LVhy jsfayx ,oa ukyh dk fuekZ.k dk;ZA | 3869500 | 2021-07-23 | Ranchi | RMC | 44 | - | 2021-03-26 | - | 2021-06-15 | - | - | - | M/s Sujeet Kumar Choudhary | - | - | - | - | -
36 | RMC | okMZ la[;k 45 ds vUrxZr fjlynkj uxj csynkj eqgYYkk] dkyh eafnj jksM] dqEgkj Vksyh ,oa jktsUnz pkSd ds lehi LySc ds lkFk ukyh dk fuekZ.k dk;ZA | 3333300 | 2021-07-23 | Ranchi | RMC | 45 | - | 2021-03-26 | - | 2021-06-15 | 2022-04-07 | 6 Months | 3299213 | MD SALIM | 1498000 | 70% | 50% | - | -
37 | RMC | okMZ la[;k 04 ds vUrxZr cM+xkbZ 'ke'kku ?kkV ls cM+xkbZ efLtn rd LySc ds lkFk ukyh ,oa 'ke'kku ?kkV ds lehi ih0 lh0 lh0 iFk dk fuekZ.k dk;ZA | 5900000 | 2021-07-23 | Ranchi | RMC | 4 | - | 2021-03-25 | - | 2021-06-29 | 2021-11-22 | 6 Months | 5065499 | M/s Randhir Kumar Singh | 5739118 | 100% | 100% | - | -
38 | RMC | okMZ la[;k 05 ds vUrxZr jksM ua0&05 esa fczfV'k ifCyd Ldwy] cM+xkbZ eq[; iFk ds lehi iFk dk fuekZ.k dk;ZA | 999900 | 2021-07-23 | Ranchi | RMC | 5 | - | 2021-03-25 | - | 2021-06-29 | 2022-01-19 | 3 Months | 732972 | M/s RB Construction |  | 100% | 100% | - | -
39 | RMC | okMZ la[;k 16 ds vUrxZr jke uxj bekjr lfj;k jksM eas vkj0 lh0 lh0 ukyh ,oaa iFk dk lq/kkj dk;ZA | 2675000 | 2021-07-23 | Ranchi | RMC | 16 | - | 2021-03-25 | - | 2021-06-29 | 2021-12-10 | 6 Months | 2649050 | MD SALIM | 2646226 | 100% | 100% | - | -
40 | RMC | okMZ la[;k 19 ds vUrxZr vkehZ dsUV ds fiNs cM+k ukyk ls gfj ij'kqjke iqfj;k ds ?kj rd vkj0 lh0 lh0 ukyh ,oa ih0 lh0 lh0 iFk dk fuekZ.k dk;ZA | 6000000 | 2021-07-23 | Ranchi | RMC | 19 | - | 2021-03-25 | - | 2021-06-29 | 2022-01-29 | 6 Months | 5999355 | Harendra Singh | 5987256 | 100% | 100% | - | -
41 | RMC | okMZ la[;k 20 ds vUrxZr xksikxat eas jhrk esfMdy ds ?kj ls txnh'k th ds ?kj gksrs dkes'ojukFk dkWEiysDl rd vkj0 lh0 ukyh ,oa I;knk Vksyh esa 'kEHkq vxzoky ds ?kj ls ctjax cyh eafnj rd iFk pkSM+hdj.k dk dk;ZA | 5820000 | 2021-07-23 | Ranchi | RMC | 20 | - | 2021-03-25 | - | 2021-06-29 | 2021-11-16 | 6 Months | 5092846 | Anand Kumar | 5695240 | 100% | 100% | - | -
42 | RMC | okMZ la[;k 37 ds vUrxZr txzukFkiqj pkSd ls iVsy uxj ,oa ekSlhckM+h ch0 ,l0 ,u0 ,y0 ,DlpsUt ls 'kadj ds ?kj rd ih0 lh0 lh0 iFk] fCkVqfeul iFk ,oa ukyh dk fuekZ.k dk;ZA | 5000000 | 2021-07-23 | Ranchi | RMC | 37 | - | 2021-03-25 | - | 2021-06-29 | 2021-10-26 | 6 Months | 4999859 | Vivek Kumar | 4971776 | 100% | 100% | - | -
43 | RMC | okMZ la[;k 39 ds vUrxZr [kVky ,l0 Vh0 jksM gksrs gq;s iVsy eSnku ls bUnzk Dyc rd ih0 lh0 lh0 iFk ,oa vkj0 lh0 lh0 ukyh dk fuekZ.k dk;ZA | 5000000 | 2021-07-23 | Ranchi | RMC | 39 | - | 2021-03-25 | - | 2021-06-29 | 2021-11-18 | 6 Months | 4950383 | M/s Prakash Enterprises | 4138853 | 100% | 95% | - | -
44 | RMC | okMZ la[;k 43 ds vUrxZr ukWFkZ vkWfQl ikM+k esa ,0 th0 pkSd gkssrs gq;s vjk/kuk vikVZesUV] fjHkj CkSad] eSW=h bUdysc iFk] ckfjd Vksyh] beyh Vksyh] d`".kk vikVZesUV] vUFkksuh pkSd] txthr bUdysc rd vkj0 lh0 lh0 ukyh ,oa fcVqfeul iFk dk fuekZ.k dk;ZA | 15500000 | 2021-07-23 | Ranchi | RMC | 43 | - | 2021-03-25 | - | 2021-06-29 | 2022-02-07 | 9 Months | 12759072 | Rohan Ritik Const. Pvt. Ltd. | 4604553 | 50% | 40% | - | -
45 | RMC | okMZ la[;k 49 ds vUrxZr lkdsr uxj esa ldqUryk >k ds ?kj ls eq[; iFk rd rd ih0 lh0 lh0 iFk ,oa vkj0 lh0 lh0 ukyh dk fuekZ.k dk;ZA | 2000000 | 2021-07-23 | Ranchi | RMC | 49 | - | 2021-03-25 | - | 2021-06-29 | 2021-12-09 | 6 Months | 1596960 | M/s Rai Construction | 1815382 | 100% | 100% | - | -
46 | RMC | okMZ la[;k 36 ds vUrxZr lo0 ea=h gkth gqlSu valkjh ds ?kj gksrs gq;s eq[; ukyk ls eq[; iFk iqUnkx es vkj0 lh0 lh0 ukyh dk fuekZ.k dk;ZA | 6847411 | 2021-07-23 | Ranchi | RMC | 36 | - | 2021-06-11 | - | 2021-06-29 | 2021-12-16 | 6 Months | 5272007 | Manu Rai | 0 | - | - | - | -
47 | RMC | okMZ la[;k 16 ds vUrxZr eq[; ukyk ls <qyq ds ?kj ls flrkjk ds ?kj gksrs gq;s eks0 eqerkt ds ?kj ls eks0 fQjkst ds ?kj rd ,oa ijost bysDVªhd ls ccy cDlk ds ?kj rd ukyh dk fuekZ.k dk;ZA | 2774000 | 2021-07-23 | Ranchi | RMC | 16 | - | - | - | 2021-06-29 | - | 6 Months | - | SOHAIL ALAM | - | - | - | - | -
48 | RMC | jkWph uxj fuxe {ks=kUrxZr eksjkcknh eSnku dSEil esa yS.MLdsfiax ,oa isHkj CykWd yxkus dk dk;ZA | 10836915 | 2021-07-23 | Ranchi | RMC | RMC | - | - | - | 2021-07-06 | 2022-01-20 | 9 Months | 8674952 | M/s S.K Enterpirses | 3665758 | 35% | 15% | - | -
49 | RMC | okMZ la[;k 17 ds vUrxZr d';i vkbZ gkWfLiVy ds lkeus ih0 ,u0 ckWl dEikm.M esa vkj0 lh0 lh0 ukyh ,oa iFk dk lq/kkj dk;ZA | 5940514 | 2021-07-23 | Ranchi | RMC | 17 | - | 2019-10-31 | - | 2021-07-06 | 2021-11-22 | 6 Months | 5929957 | Shashi Prakash | 4469198 | 100% | 90% | - | -
50 | RMC | okMZ la[;k 15 ds vUrxZr dksudk jksM ,oa MkW0 QrsmYykg jksM ds fofHkUu xfy;ksa esa vkj0 lh0 ukyh ,oa iFk dk lq/kkj dk;ZA | 37800000 | 2021-07-23 | Ranchi | RMC | 15 | - | 2021-03-25 | - | 2021-06-17 | 2021-12-09 | 12 Months | 37800000 | M/s Shivam Construction | 17287577 | 50% | 50% | - | -
51 | RMC | jkWph uxj fuxe {ks=kUrxZRk eksjkcknh eSnku dSEil dk iquZfodkl dk dk;ZA | 47782352 | 2021-07-23 | Ranchi | RMC | RMC | - | - | - | 2021-07-06 | 2021-11-09 | 12 Months | 47782411 | Awadhesh Singh Construction Pvt. Ltd. | 0 | 15% | - | - | -
52 | RMC | Construction of Bituminous road for various roads of suryapuri, Bank office colony and devi mandap road under Ward No- 31 | 10344900 | 2022-11-15 | Ranchi | RMC | 31 | - | - | - | 2022-02-04 | 2022-10-11 | 9 Months | 10316078 | Jainendra Enterprises | 0 | - | - | - | -
53 | RMC | Improvement of Road with Bituminous surface & PCC and Construction of RCC Drain at Sultan lane from locl petrol pump to purulia road via kilkhana jama masjid and at idrish colony from purulia road to masjid a gausia in Ward No- 11 | 24371072 | 2022-11-15 | Ranchi | RMC | 11 | - | 2021-12-17 | - | 2022-07-26 | 2022-11-29 | 9 Months | 19689390 | M/s Gopal Lohia | 0 | - | - | - | -
54 | RMC | Improvement of Road with Bituminous & PCC Surface and construction of RCC Drain from Upar Kocha to marianist (English Medium) school under Ward No- 12 | 20442620 | 2022-11-15 | Ranchi | RMC | 12 | - | 2021-11-29 | - | 2022-07-26 | 2022-11-29 | 9 Months | 16137405 | M/s Gopal Lohia | 0 | - | - | - | -
55 | RMC | Construction of RCC Drain at Hinoo Indra Place to CPWD Office via Hathikhana Pool and Hinoo Thakur Mohalla from Kilwarn Colony via Janardhan Dubey ji to House under Ward No- 49 | 22584200 | 2022-11-15 | Ranchi | RMC | 49 | - | 2022-07-19 | - | 2022-07-21 | 2022-11-09 | 9 Months | 16639942 | Jitendra Prasad Const. LLP | 0 | - | - | - | -
56 | RMC | Construction of RCC Drain from sani mandir to saboo rickshaw traders and garykhana park kartsarai road under Ward No- 20 | 17707724 | 2022-11-15 | Ranchi | RMC | 20 | - | 2022-03-25 | - | 2022-07-18 | 2022-11-23 | 9 Months | 14219281 | M/s Murarka Construction | 0 | - | - | - | -
57 | RMC | Construction of RCC Drain at different lane of johar nagar under Ward No- 36 | 16223240 | 2022-11-15 | Ranchi | RMC | 36 | - | - | - | 2022-08-03 | 2022-11-11 | 9 Months | 12978593 | Sri Ajay Verma | 0 | - | - | - | -
58 | RMC | Installation of slab and construction of open big drain from vasundhra mega mart to upkar nagar Construction of Drain at rhakur jee lane Rahat Colony near Karam Chowk and Behind BCD Quarter Installation of Paver Block at ashok kunj improvement of PCC Road at Ashok Kunj in different lane under Ward No- 25 and 26 | 18523327 | 2022-11-15 | Ranchi | RMC | 25/26 | - | 2022-02-10 | - | 2022-06-01 | 2022-11-29 | 9 Months | 14448317 | M/s Amrendra Singh | 0 | - | - | - | -
59 | RMC | Beautification & conservation of Bada Nala near from shrinagar to anand nagar boundary wall work for masna near anand nagar bada nala construction of RCC Drain at anand nagar and bhawani nagar construction of shade for masna near anand nagar construction of shade for masna near anand nagar bada nala & HYDT & Plantation under Ward No- 27 | 24441127 | 2022-11-15 | Ranchi | RMC | 27 | - | 2019-02-21 | - | 2022-05-25 | 2022-11-02 | 9 Months | 24441123 | Anuj Kumar Hembrom | 0 | - | - | - | -