## Sheet1
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC Road at khijurtola ali nagar main road to house of md firoj under ward no-05.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
2 5.1.1 J.B.C.D | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling, ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. Extra for earthwork in hard soil as per specification & direction of E/I.(vide classification of soil item-B) | 50.98 | m3 | 151.82 | 7739.7836
3 4/M004 | Providing,supplying & spreding of stone dust in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of materials, labour,royality and taxes all complete as per specification and direction of E/I ( Mode of measurment compacted volume.) | 16.99 | m3 | 347.85 | 5909.9715
4 5.6.8 J.B.C.D | Supplying and laying (properly as per design and drawing) rip-rap with good quality of boulders duly packed including the cost of materials, royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 27.87 | m3 | 1756.4 | 48950.868
5 J.B.C.D 5.3.1.1 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shutering All work upto pilith level.1:1.5.3(1 Cement:1.5 coarse sand(zone iii):3graded stone Aggregate 20mm nomial size. | 33.98 | m3 | 4961.73 | 168599.5854
6 J.B.C.D 5.3.17.1 | Centering and shuttering including strutting , etc and removel of form for foundation, footings bases of column etc for mass concrete. | 18.59 | m2 | 194.5 | 3615.755
7 | Carriage of Materials
i | Sand (Lead 49 KM) | 14.61 | m3 | 848.82 | 12401.2602
ii | Sand Local / Dust(Lead 22 KM) | 16.99 | m3 | 447.06 | 7595.5494
iii | Stone Chips (Lead 22 KM) | 29.23 | m3 | 447.06 | 13067.5638
iv | BOULDER-LEAD-( 36 KM ) | 27.87 | m3 | 679.66 | 18942.1242
v | Earth (Lead 01 KM) | 50.98 | m3 | 117.54 | 5992.1892
|  |  |  | TOTAL | 292814.6503
|  |  |  | GST (18%) | 52706.6371
345521.2874
|  |  |  | L. CESS (1%) | 3455.2129
|  |  |  | TOTAL | 348976.5002

## Sheet2
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC Drain in Gali no-05 and near famous medical at molana azad colony under ward no 12.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site and head load as per specification and direction E/I | 3 | Each | 326.85 | 980.55
2 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling, ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. | 52.14 | m3 | 151.82 | 7915.8948
3 4/M004 | Providing,supplying & spreding of stone dust in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of materials, labour,royality and taxes all complete as per specification and direction of E/I ( Mode of measurment compacted volume.) | 3.32 | m3 | 347.85 | 1154.862
4 5.6.8 | Supplying and laying (properly as per design and drawing) rip-rap with good quality of boulders duly packed including the cost of materials, royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 8.14 | m3 | 1756.4 | 14297.096
5 5.3.10 | Reinforced cement concrete work in walls (any thickness) including atteched plasters, buttresses plinth and string course, fillets, columns, pillars, piers, abutments, post, and struts etc above plinth level up to floor five level, excluding the cost of centering, shuttering, finishing and reinforcement.RCC 1:1.5:3 (1 Cement : 1.5 coarse sand zone(III): 3 graded stone aggregate 20mm nominal size) | 23.02 | m3 | 6082.45 | 140017.999
6 5.3.11 | Renforced cement conrete work in beams, suspended floors, having slopeup to 15' landing, balconies, shelves, chajjas, lintels, bands, plain windowsill ---------do----do-------E/I 1:1.5:3 (1 Cement : 1.5 coarse sand zone(III): 3 graded stone aggregate 20mm nominal size) | 9.76 | m3 | 6308.87 | 61574.5712
7 (A)5.5.4 | Providing Tor steel reinforcement of 10 mm,12mm &16mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. 10 mm dia 40% | 1.574 | M.T. | 83314.02 | 131136.2675
8 (B)5.5.5(a) | 12 mm dia 60% | 1.158 | M.T. | 82096.54 | 95067.7933
9 5.3.17.1 | Centering and Shuttering including strutting, propping etc and removal of from for Foundation , footing , bases of columns etc for mass concrete. | 113.67 | m2 | 194.5 | 22108.815
10 | Carriage of Materials
(i) | Sand (Lead 42 KM) | 14.1 | m3 | 744.66 | 10499.706
(ii) | Sand Local / Dust(Lead 25 KM) | 3.32 | m3 | 342.9 | 1138.428
(iii) | Stone Chips (Lead 25 KM) | 28.19 | m3 | 342.9 | 9666.351
(iv) | BOULDER-LEAD-( 29 KM ) | 8.14 | m3 | 570.94 | 4647.4516
(v) | Earth (Lead 01 KM) | 52.138 | m3 | 117.54 | 6128.3005
|  |  |  | TOTAL | 506334.0859
|  |  |  | GST (18%) | 91140.1355
597474.2214
|  |  |  | L. CESS (1%) | 5974.7422
|  |  |  | TOTAL | 603448.9636

## Sheet3
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC Drain at bhatti kocha upper chutiya from house of meera devi to house of gopal sahu under ward no 14.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Labour for cleaning the work site before and after work etc. | 7 | Each | 326.85 | 2287.95
2 5.1.1 J.B.C.D | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling, ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. Extra for earthwork in hard soil as per specification & direction of E/I.(vide classification of soil item-B) | 20.53 | m3 | 151.82 | 3116.8646
3 4/M004 | Providing,supplying & spreding of stone dust in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of materials, labour,royality and taxes all complete as per specification and direction of E/I ( Mode of measurment compacted volume.) | 2.37 | m3 | 347.85 | 824.4045
4 5.6.8 J.B.C.D | Supplying and laying (properly as per design and drawing) rip-rap with good quality of boulders duly packed including the cost of materials, royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 3.98 | m3 | 1756.4 | 6990.472
5 5.3.10 | Reinforced cement concrete work in walls(any thickness),including attached pilasters, buttresses,plinth and string courses,fillets columns,pillars,piers,abutments,posts and struts etc.above plinth level up to floor five level,excluding cost of centering,shuttering,finishing and reinforcement: 1:1.5:3(1 cement :1.5 coarse sand(zoneIII): 3 graded stone aggregate 20mm nominal size) | 6.86 | M³ | 6082.45 | 41725.607
6 5.3.11 | Reinforced cement concrete work in beams, suspended floors, roofs having slope up to 15 landings, balconies, shelves, chajjas, lintels, band, plain window sills, staircases and spiral stair cases above plinth level up to floor five level, excluding the cost of centering, shuttering, finishing and reinforcement: with 1.1.5.3 (1 cement :1.5 coarse sand(zoneIII): 3 graded stone aggregate 20mm nominal size) | 3.13 | M³ | 6308.87 | 19746.7631
7 J.B.C.D 5.3.17.1 | Centering and shuttering including strutting , etc and removel of form for foundation, footings bases of column etc for mass concrete. | 80.48 | m2 | 194.5 | 15653.36
8 BCD 5.5.4 5.5.5 | Providing tor steel reinforcement of 8mm. dia. rods as per approved design and drawing with cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position (excluding carriage of bars to work site) all complete as per building specification and direction of E/l. TMT Fe 500 {(Only Valid for TATA(Tiscon), SAIL, JSPL, Electrosteel steels ltd.Bokaro and Vizag(RINL)} . And above dia. (i) 8 mm dia | 0.262 | MT | 83314.02 | 21828.2732
| (ii) 10 mm dia | 0.38 | MT | 82096.54 | 31196.6852
9 | Carriage of Materials
i | Sand (Lead 42 KM) | 4.3 | m3 | 744.66 | 3202.038
ii | Sand Local / Dust(Lead 15 KM) | 2.37 | m3 | 342.9 | 812.673
iii | Stone Chips (Lead 15 KM) | 8.59 | m3 | 342.9 | 2945.511
iv | BOULDER-LEAD-( 29 KM ) | 3.98 | m3 | 570.94 | 2272.3412
v | Earth (Lead 01 KM) | 20.53 | m3 | 117.54 | 2413.0962
|  |  |  | TOTAL | 155016.039
|  |  |  | GST (18%) | 27902.887
182918.9261
|  |  |  | L. CESS (1%) | 1829.1893
|  |  |  | TOTAL | 184748.1153

## Sheet4
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC road at bhatti kocha upper chutiya from house of meera devi to house of gopal sahu under ward no 14.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Labour for cleaning the work site before and after work etc. | 10 | Each | 326.85 | 3268.5
2 5.1.1 J.B.C.D | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling, ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. Extra for earthwork in hard soil as per specification & direction of E/I.(vide classification of soil item-B) | 30.36 | m3 | 151.82 | 4609.2552
3 4/M004 | Providing,supplying & spreding of stone dust in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of materials, labour,royality and taxes all complete as per specification and direction of E/I ( Mode of measurment compacted volume.) | 11.33 | m3 | 347.85 | 3941.1405
4 5.6.8 J.B.C.D | Supplying and laying (properly as per design and drawing) rip-rap with good quality of boulders duly packed including the cost of materials, royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 19.04 | m3 | 1756.4 | 33441.856
5 J.B.C.D 5.3.1.1 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shutering All work upto pilith level.1:1.5.3(1 Cement:1.5 coarse sand(zone iii):3graded stone Aggregate 20mm nomial size. | 22.66 | m3 | 4961.73 | 112432.8018
6 J.B.C.D 5.3.17.1 | Centering and shuttering including strutting , etc and removel of form for foundation, footings bases of column etc for mass concrete. | 18.59 | m2 | 194.5 | 3615.755
7 | Carriage of Materials
i | Sand (Lead 42 KM) | 9.74 | m3 | 744.66 | 7252.9884
ii | Sand Local / Dust(Lead 15 KM) | 11.33 | m3 | 342.9 | 3885.057
iii | Stone Chips (Lead 15 KM) | 19.48 | m3 | 342.9 | 6679.692
iv | BOULDER-LEAD-( 29 KM ) | 19.04 | m3 | 570.94 | 10870.6976
v | Earth (Lead 01 KM) | 30.36 | m3 | 117.54 | 3568.5144
|  |  |  | TOTAL | 193566.2579
|  |  |  | GST (18%) | 34841.9264
228408.1843
|  |  |  | L. CESS (1%) | 2284.0818
|  |  |  | TOTAL | 230692.2662

## Sheet5
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC road at pakka kuwa chhat talab from house of madan lodge to shankar mahto under Ward No- 14
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Labour for cleaning the work site before and after work etc. | 9 | Each | 326.85 | 2941.65
2 5.1.1 J.B.C.D | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling, ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. Extra for earthwork in hard soil as per specification & direction of E/I.(vide classification of soil item-B) | 83.26 | m3 | 151.82 | 12640.5332
3 4/M004 | Providing,supplying & spreding of stone dust in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of materials, labour,royality and taxes all complete as per specification and direction of E/I ( Mode of measurment compacted volume.) | 39.5 | m3 | 347.85 | 13740.075
4 5.6.8 J.B.C.D | Supplying and laying (properly as per design and drawing) rip-rap with good quality of boulders duly packed including the cost of materials, royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 19.99 | m3 | 1756.4 | 35110.436
5 J.B.C.D 5.3.1.1 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shutering All work upto pilith level.1:1.5.3(1 Cement:1.5 coarse sand(zone iii):3graded stone Aggregate 20mm nomial size. | 23.79 | m3 | 4961.73 | 118039.5567
6 J.B.C.D 5.3.17.1 | Centering and shuttering including strutting , etc and removel of form for foundation, footings bases of column etc for mass concrete. | 13.01 | m2 | 194.5 | 2530.445
7 | Carriage of Materials
i | Sand (Lead 42 KM) | 10.23 | m3 | 744.66 | 7617.8718
ii | Sand Local / Dust(Lead 15 KM) | 39.5 | m3 | 342.9 | 13544.55
iii | Stone Chips (Lead 15 KM) | 20.46 | m3 | 342.9 | 7015.734
iv | BOULDER-LEAD-( 29 KM ) | 19.99 | m3 | 570.94 | 11413.0906
v | Earth (Lead 01 KM) | 83.26 | m3 | 117.54 | 9786.3804
|  |  |  | TOTAL | 234380.3227
|  |  |  | GST (18%) | 42188.4581
276568.7808
|  |  |  | L. CESS (1%) | 2765.6878
|  |  |  | TOTAL | 279334.4686

## Sheet6
RANCHI MUNICIPAL CORPORATION CONSTRUCTION OF RCC DRAIN AND CULVERT AT SUKHDEV NAGER FROM AMIT HOUSE NEAR MANDIR TO GUDUN HOUSE UNDER WARD NO 31.
BILL OF QUANTITY
Work Name:- la[ksnso uxj esa vfer ds ?kj ls xqMu ds ?kj rd vkj0 lh0 lh0 ukyh ,oa dYkHkVZ dk fuekZ.k dk;ZA
Sl No. | PARTICULARS OR ITEM OF WORKS | QUANTITY | UNIT | RATE (in Rs.) | AMOUNT(in Rs.)
1 | Providing Mandays for site clearence, unskilled labour | 4 | NO | 326.85 | 1307.4
2. 5.10.2 JBCD | Dismantling of PCC work ……do….all complete. | 6.37 | M³ | 955.89 | 6089.02
3. 5.1.1. JBCD | Earthwork in excavation in foundation trenches in ordinary soil (vide classification of soil item -A) and disposal of excavated earth as obtained to a distance upto 50 m including all lifts,levelling,ramming the foundation trenches,removing roots of trees,shrubs all complete as per approved design,building specification and direction of E/I. | 52.71 | M³ | 151.82 | 8002.43
4. 5.1.10 JBCD | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of materials , labour , royalty and taxes all complete as per specification and direction of E/I. ( Mode of measurement compacted volume. ) | 5.78 | M³ | 589.51 | 3407.37
5. 8.6.8 JBCD | Supplying and laying (properly as per design and drawing) rip-rap with good quality of boulders duly packed including the cost of materials, royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 9.71 | M³ | 1756.4 | 17054.64
6. 5.3.10 JBCD | Reinforced cement concrete work in walls (any thickness),including attached pilasters, buttresses, plinth and string courses, fillets, columns,pillars, piers, abutments, posts and struts etc.above plinth level upto to five level, excluding the cost of centering, shuttering, finishing and reinforcement with 1:1½:3 (1 cemet : 1½ coarse sand (zone-iii) : 3 graded stone aggregate 20mm nominal size ) | 22.21 | M³ | 6082.45 | 135091.21
7. 5.3.11 JBCD | Reinforced cement concrete work in beam, suspended floors, roofs having slope up to 15° landing,balconies, shelves, chajjas, lintel, bands, plain window sills, staircases and spiral stair cases above plinth level up to floor five level, excluding the cost of centering, shuttering, finishing and reinfocement, with 1:1.5:3(1 cement : 1.5 coarse sand(zone-iii) : 3 graded stone aggregate 20mm nominal size) | 11.88 | M³ | 6308.87 | 74949.38
8. 5.5.4, 5.5.5 (a,b) JBCD | Providing Tor steel reinforcement of 8mm , 10mm and 12mm dia rods as per approved …...........do…..........TMT Fe 500(Only valid for Tata (Tiscon),SAIL,JSPL,Electrosteel Steels Ltd, Bokaro and Vizag(RINL) |  | M³ |  | 0
(a) | 8mm ф @38% | 1.1 | MT | 83314.02 | 91645.42
(b) | 10 mm ф @62% | 1.79 | MT | 82096.54 | 146952.81
9 5.3.17.1 JBCD | Centering and shuttering including strutting, propping etc. and removal of from for Foundations,footings, bases of columns, etc. for mass concrete. | 258.07 | M² | 194.5 | 50194.62
10 | CARRIAGE OF MATERIALS
| (i) SAND-LEAD-49km | 14.66 | M³ | 848.82 | 12443.7
| (ii) SAND LOCAL-LEAD-14 KM | 5.78 | M³ | 328.02 | 1895.96
| (iii)STONE CHIPS-LEAD-22 km | 29.32 | M³ | 447.06 | 13107.8
| (iv) STONE BOULDER 36 KM | 9.71 | M³ | 679.66 | 6599.5
| (v) EARTH-LEAD-1km | 52.71 | M³ | 117.54 | 6195.53
|  |  |  | Total | 574936.79
|  | Add 18% GST |  |  | 103488.62
|  | Total |  |  | 678425.41
|  | Add 1% Labour cess |  |  | 6784.25
|  | Total |  |  | 685209.66

## Sheet7
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
NAME OF WORK :- IMPROVEMENT OF P.C.C. ROAD AT SUKHDEO NAGAR FROM CULVERT TO GUDAN HOUSE UNDER WARD NO.31
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1. 5.3.1.1JBCD | Providing and laying in position cement concrete of specified grade excluding the cost of excluding cost of centring,shuttring-All work up to plinth level;1:1.5:3(1cement:1.5 coarse sand(zone-lll):3 grade stone agreegate 20mm nominal size)..........do…..all complete as per specification and direction of E/I. | 35.68 | M3 | 4961.73 | 177034.53
2. 5.3.17.1 JBCD | Centring and shuttring including strutting,propping etc. and removal of from for Foundation, footings,bases of column,etc for mass concrete | 23.43 | M2 | 194.5 | 4557.14
7 | CARRIAGE OF MATERIALS |  | M3
i | (i).SAND-LEAD-49km | 15.34 | M3 | 848.82 | 13020.9
ii | (ii)CHIPS-LEAD-22km | 30.68 | M3 | 447.06 | 13715.8
|  | Total |  |  | 208328.37
|  | Add 18% GST |  |  | 37499.11
|  | Total |  |  | 245827.48
|  | Add 1% Labour cess |  |  | 2458.27
|  | G.Total |  |  | 248285.75

## Sheet8
RANCHI MUNCIPAL CORPORATION RANCHI CONNSTRUCTION OF RCC DRAIN AT PATHAK MOHALLA FROM TO GLOBAL SCHOOL UNDER WARD NO 31
BILL OF QUANTITY
Sl No. | PARTICULARS OR ITEM OF WORKS | QUANTITY | UNIT | RATE (in Rs.) | AMOUNT(in Rs.)
1. 5.1.1. | Earthwork in excavation in foundation trenches in ordinary soil (vide classification of soil item -A) and disposal of excavated earth as obtained to a distance upto 50 m including all lifts,levelling,ramming the foundation trenches,removing roots of trees,shrubs all complete as per approved design,building specification and direction of E/I. | 64.64 | No. | 151.82 | 9813.6448
2. 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of materials , labour , royalty and taxes all complete as per specification and direction of E/I. ( Mode of measurement compacted volume. ) | 5.1 | M³ | 589.51 | 3006.501
3. 5.6.8 | Supplying and laying (properly as per design and drawing )rip-rap with good quality of boulders duly packed including the cost of materials,royalty all taxes etc.but excluding the cost of carriage, all complete as per specification and direction of E/I. | 8.56 | M³ | 1756.4 | 15034.784
4. 5.3.10 | Reinforced cement concrete work in walls (any thickness),including attached pilasters, buttresses, plinth and string courses, fillets, columns,pillars, piers, abutments, posts and struts etc.above plinth level upto to five level, excluding the cost of centering, shuttering, finishing and reinforcement with 1:1½:3 (1 cemet : 1½ coarse sand (zone-iii) : 3 graded stone aggregate 20mm nominal size ) | 20.32 | M² | 6082.45 | 123595.384
5 5.3.11 | Reinforced cement concrete work in beam, suspended floors, roofs having slope up to 15° landing,balconies, shelves, chajjas, lintel, bands, plain window sills, staircases and spiral stair cases above plinth level up to floor five level, excluding the cost of centering, shuttering, finishing and reinfocement, with 1:1.5:3(1 cement : 1.5 coarse sand(zone-iii) : 3 graded stone aggregate 20mm nominal size) | 10.2 | M³ | 6308.87 | 64350.474
6 5.5.5+ 5.5.4 | Providing Tor steel reinforcement of 8mm, 10mm and 12mm dia rods as per approved …...........do…..........TMT Fe 500(Only valid for Tata (Tiscon),SAIL,JSPL,Electrosteel Steels Ltd, Bokaro and Vizag(RINL)
| (i) 8 mm ia bar | 0.983 | MT | 83314.02 | 81897.6817
| (i) 10 mm ia bar | 1.603 | M³ | 82096.54 | 131600.7536
7 5.3.17.1 | Centering and shuttering including strutting, propping etc. and removal of from for Foundations,footings, bases of columns, etc. for mass concrete. | 245.35 | M³ | 194.5 | 47720.575
CARRIAGE OF MATERIALS
| (i) SAND-LEAD-49km | 13.13 | MT | 848.82 | 11145.0066
| (ii) SAND LOCAL-LEAD-14 KM | 5.1 | M³ | 328.02 | 1672.902
| (iii) CHIPS-LEAD-22 km | 26.25 | M³ | 447.06 | 11735.325
| (iv) BOULDER-LEAD-36 km | 8.56 | N0. | 679.66 | 5817.8896
| (v) EARTH-LEAD-1km | 64.64 | M³ | 117.54 | 7597.7856
| TOTAL |  |  |  | 514988.7069
| Add 18% GST |  |  |  | 92697.97
|  | TATAL |  |  | 607686.6769
|  | Add 1% Labour cess |  |  | 6076.87
|  | TOTAL |  |  | 613763.5469

## Sheet9
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC Drain at hatia akta nagar road no-01 house of birander kumar to nadan palace under ward no-52.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling, ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. | 34.52 | m3 | 151.82 | 5240.8264
2 4/M004 | Providing,supplying & spreding of stone dust in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of materials, labour,royality and taxes all complete as per specification and direction of E/I ( Mode of measurment compacted volume.) | 1.7 | m3 | 347.85 | 591.345
3 5.6.8 | Supplying and laying (properly as per design and drawing) rip-rap with good quality of boulders duly packed including the cost of materials, royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 4.35 | m3 | 1756.4 | 7640.34
4 5.3.10 | Reinforced cement concrete work in walls (any thickness) including atteched plasters, buttresses plinth and string course, fillets, columns, pillars, piers, abutments, post, and struts etc above plinth level up to floor five level, excluding the cost of centering, shuttering, finishing and reinforcement.RCC 1:1.5:3 (1 Cement : 1.5 coarse sand zone(III): 3 graded stone aggregate 20mm nominal size) | 13.81 | m3 | 6082.45 | 83998.6345
5 5.3.11 | Renforced cement conrete work in beams, suspended floors, having slopeup to 15' landing, balconies, shelves, chajjas, lintels, bands, plain windowsill ---------do----do-------E/I 1:1.5:3 (1 Cement : 1.5 coarse sand zone(III): 3 graded stone aggregate 20mm nominal size) | 5.31 | m3 | 6308.87 | 33500.0997
6 | Providing Tor steel reinforcement of 10 mm,12mm &16mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. 08mm dia 40% | 0.626 | M.T. | 83314.02 | 52154.5765
(B)5.5.5(a) | 10mm dia 60% | 0.939 | M.T. | 82096.54 | 77088.6511
7 5.3.17.1 | Centering and Shuttering including strutting, propping etc and removal of from for Foundation , footing , bases of columns etc for mass concrete. | 125.46 | m2 | 194.5 | 24401.97
8 | Carriage of Materials
(i) | Sand (Lead Upto 42 km) | 8.22 | M3 | 744.66 | 6121.1052
(ii) | Stone Dust (Lead 15 KM) | 1.7 | M3 | 342.9 | 582.93
(iii) | Stone Boulder (Lead 29 KM) | 4.35 | M3 | 570.94 | 2483.589
(iv) | Stone Chips (Lead 15KM) | 16.45 | M3 | 342.9 | 5640.705
(v) | Earth (Lead 01 KM) | 34.52 | M3 | 117.54 | 4057.4808
|  |  |  | TOTAL | 303502.2532
|  |  |  | GST (18%) | 54630.4056
358132.6588
|  |  |  | L. CESS (1%) | 3581.3266
|  |  |  | TOTAL | 361713.9853